## Planification
Project Phases | March |  |  |  | April |  |  |  | May | Mayo | Junio | Julio | June | Mayo | Junio | Julio | July | Mayo | Junio | Julio | August | Mayo | Junio | Julio | September | Mayo | Junio | Julio | October | Mayo | Junio | Julio | November | Mayo | Junio | Julio | December | Mayo | Junio | Julio
| w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4
1. Research & Planning
1.1 Project Planning: objectives | bar: w1
1.2 State of the Art Research | bar: w1 to w2
1.3 UAV Study | bar: w3
1.4 ML Study for Object Recognition | bar: w4
1.5 Architecture & Project Mock-Up | bar: w1 to w2
2. Development of the UAV
2.1 Hardware Selection | bar: w3 to w4
2.2 Assembly | bar: w1 to w2
2.3 Flight Testing | bar: w3 to w4
3. Development of the Server & ML
3.1 Server Architecture | bar: w3 to w4
3.2 Development of the Server | bar: w1 to w4
3.3 Development of the On-Board System | bar: w1 to w4
4. Final Testing and Result Gathering
4.1 Integration of the System | bar: w1 to w4
4.2 Flight Testing | bar: w1; w3
4.3 Results Study | bar: w2; w4
5. Structure of the document
5.1 Planification | bar: w1
5.2 Writing | bar: w2 to w1
5.3 Revision & Updates | bar: w2 to w4